## Overview
A-idol — Project WBS & Test Plan
Version 1.0.0 ¦ Created 2026-04-18 ¦ Owner: Gray Kim
Item | Value
Project | A-idol (AI Idol Fandom Platform)
Mobile | React Native 0.74 (iOS 14+, Android 10+)
CMS | React 18 + Vite + shadcn/ui
Backend | NestJS 10 + Prisma 5
Database | PostgreSQL 16 + Redis 7
Architecture | Clean Architecture (Entity / UseCase / Adapter / Infra)
Start Date | 2026-04-20
MVP GA | 2026-08-29
Duration | 19 weeks
Total Effort | ~146 person-days (core dev)
Team Size | 8 (PM1, BE2, Mobile2, CMS1, QA1, DevOps1)
Sheet Map
WBS | Work Breakdown Structure — all tasks (T-001 …)
Milestones | Milestone table with target dates & exit criteria
TestCases | Unit/integration test cases (TC-/ITC-)
API | REST API inventory
Screens | Screen inventory (Mobile + CMS)
Risks | Risk register
KPI | Success metrics tracking

## WBS
ID | Task | Phase | Area | Priority | Effort (d) | Depends On | Assignee | GitHub Issue | Branch | Start | End | Status
T-001 | Monorepo scaffolding (pnpm workspace) | Setup | infra | P0 | 1 |  | DevOps |  | feature/001-monorepo | 2026-04-20 | 2026-04-20 | Backlog
T-002 | Shared domain package (@a-idol/domain) | Setup | shared | P0 | 2 | T-001 | Backend |  | feature/002-shared-domain | 2026-04-21 | 2026-04-22 | Backlog
T-003 | NestJS backend skeleton + config/logging | Setup | backend | P0 | 2 | T-001 | Backend |  | feature/003-nest-skeleton | 2026-04-21 | 2026-04-22 | Backlog
T-004 | PostgreSQL + Redis docker-compose, Prisma init | Setup | backend | P0 | 1 | T-003 | Backend |  | feature/004-db-compose | 2026-04-23 | 2026-04-23 | Backlog
T-005 | RN app scaffolding + TS strict + nav | Setup | mobile | P0 | 2 | T-001 | Mobile |  | feature/005-rn-skeleton | 2026-04-21 | 2026-04-22 | Backlog
T-006 | CMS (Vite/React) scaffolding + auth shell | Setup | cms | P0 | 2 | T-001 | CMS |  | feature/006-cms-skeleton | 2026-04-21 | 2026-04-22 | Backlog
T-007 | GitHub Actions CI (lint/test/build) | Setup | devops | P0 | 2 | T-003,T-005,T-006 | DevOps |  | feature/007-ci | 2026-04-24 | 2026-04-27 | Backlog
T-008 | Environments + secrets + ECS skeleton | Setup | devops | P0 | 3 | T-004,T-007 | DevOps |  | feature/008-infra | 2026-04-28 | 2026-04-30 | Backlog
T-009 | Identity module — signup/login (email+social) | Setup | backend | P0 | 4 | T-004 | Backend |  | feature/009-identity | 2026-04-24 | 2026-04-29 | Backlog
T-010 | Mobile auth screens + keychain | Setup | mobile | P0 | 3 | T-005,T-009 | Mobile |  | feature/010-mobile-auth | 2026-04-30 | 2026-05-02 | Backlog
T-011 | CMS auth + RBAC base | Setup | cms | P0 | 2 | T-006,T-009 | CMS |  | feature/011-cms-auth | 2026-04-30 | 2026-05-01 | Backlog
T-020 | Catalog module (idols, agencies, media, schedules) | A. Catalog | backend | P0 | 4 | T-009 | Backend |  | feature/020-catalog | 2026-05-04 | 2026-05-07 | Backlog
T-021 | Fandom module (hearts, follows) | A. Catalog | backend | P0 | 2 | T-020 | Backend |  | feature/021-fandom | 2026-05-08 | 2026-05-11 | Backlog
T-022 | Fan club + membership domain | A. Catalog | backend | P0 | 3 | T-020 | Backend |  | feature/022-fanclub | 2026-05-12 | 2026-05-14 | Backlog
T-023 | Mobile idol list & detail screens | A. Catalog | mobile | P0 | 4 | T-020 | Mobile |  | feature/023-idol-screens | 2026-05-08 | 2026-05-13 | Backlog
T-024 | Mobile heart/follow interactions | A. Catalog | mobile | P0 | 2 | T-021 | Mobile |  | feature/024-heart-follow | 2026-05-14 | 2026-05-15 | Backlog
T-025 | Mobile fan club join flow | A. Catalog | mobile | P0 | 3 | T-022 | Mobile |  | feature/025-fanclub-join | 2026-05-18 | 2026-05-20 | Backlog
T-026 | CMS Idol/Agency CRUD | A. Catalog | cms | P0 | 5 | T-020 | CMS |  | feature/026-cms-idol | 2026-05-08 | 2026-05-14 | Backlog
T-027 | CMS Auto-message template manager | A. Catalog | cms | P0 | 3 | T-022 | CMS |  | feature/027-cms-auto-msg | 2026-05-18 | 2026-05-20 | Backlog
T-028 | Seed data: 99 idols + 1 agency | A. Catalog | content | P0 | 2 | T-026 | Content |  | feature/028-seed | 2026-05-21 | 2026-05-22 | Backlog
T-040 | Chat module (rooms, messages) + WS gateway | B. Chat & Shop | backend | P0 | 5 | T-022 | Backend |  | feature/040-chat | 2026-05-25 | 2026-05-29 | Backlog
T-041 | Chat coupon logic + daily reset job | B. Chat & Shop | backend | P0 | 3 | T-040 | Backend |  | feature/041-chat-coupon | 2026-06-01 | 2026-06-03 | Backlog
T-042 | Auto-message dispatcher (BullMQ cron) | B. Chat & Shop | backend | P0 | 3 | T-041 | Backend |  | feature/042-auto-msg | 2026-06-04 | 2026-06-08 | Backlog
T-043 | Mobile chat room UI + WS client | B. Chat & Shop | mobile | P0 | 5 | T-040 | Mobile |  | feature/043-chat-ui | 2026-06-01 | 2026-06-05 | Backlog
T-044 | Commerce module (orders, receipts, IAP verify) | B. Chat & Shop | backend | P0 | 5 | T-009 | Backend |  | feature/044-commerce | 2026-06-08 | 2026-06-12 | Backlog
T-045 | Photo card module (sets, items, draw) | B. Chat & Shop | backend | P0 | 3 | T-044 | Backend |  | feature/045-photocard | 2026-06-15 | 2026-06-17 | Backlog
T-046 | Mobile IAP integration (StoreKit/Billing) | B. Chat & Shop | mobile | P0 | 4 | T-044 | Mobile |  | feature/046-mobile-iap | 2026-06-15 | 2026-06-18 | Backlog
T-047 | Mobile photo card shop + draw + collection | B. Chat & Shop | mobile | P0 | 4 | T-045,T-046 | Mobile |  | feature/047-card-shop | 2026-06-19 | 2026-06-24 | Backlog
T-048 | Instagram share + watermark generator | B. Chat & Shop | backend+mobile | P1 | 3 | T-047 | Mobile |  | feature/048-share | 2026-06-25 | 2026-06-29 | Backlog
T-049 | CMS Photo Card Sets manager | B. Chat & Shop | cms | P0 | 3 | T-045 | CMS |  | feature/049-cms-cards | 2026-06-18 | 2026-06-22 | Backlog
T-060 | Audition + Round domain | C. Audition | backend | P0 | 3 | T-020 | Backend |  | feature/060-audition | 2026-06-30 | 2026-07-02 | Backlog
T-061 | VoteRule + weight validator | C. Audition | backend | P0 | 2 | T-060 | Backend |  | feature/061-vote-rule | 2026-07-03 | 2026-07-06 | Backlog
T-062 | Vote ticket purchase flow | C. Audition | backend | P0 | 2 | T-044 | Backend |  | feature/062-vote-ticket | 2026-07-07 | 2026-07-08 | Backlog
T-063 | Cast vote use case + Redis counter | C. Audition | backend | P0 | 3 | T-060,T-062 | Backend |  | feature/063-cast-vote | 2026-07-09 | 2026-07-13 | Backlog
T-064 | Ranking aggregation cron | C. Audition | backend | P0 | 3 | T-063 | Backend |  | feature/064-ranking | 2026-07-14 | 2026-07-16 | Backlog
T-065 | Mobile audition overview + round vote screens | C. Audition | mobile | P0 | 5 | T-063 | Mobile |  | feature/065-audition-mobile | 2026-07-14 | 2026-07-20 | Backlog
T-066 | Mobile vote ticket shop | C. Audition | mobile | P0 | 2 | T-062 | Mobile |  | feature/066-ticket-shop | 2026-07-21 | 2026-07-22 | Backlog
T-067 | CMS Audition/Round/VoteRule managers | C. Audition | cms | P0 | 5 | T-060,T-061 | CMS |  | feature/067-cms-audition | 2026-07-07 | 2026-07-13 | Backlog
T-068 | CMS Dashboard (votes/revenue/users) | C. Audition | cms | P0 | 5 | T-044,T-063 | CMS |  | feature/068-dashboard | 2026-07-23 | 2026-07-29 | Backlog
T-080 | Observability (OTel, Sentry, Datadog) | D. Stabilize | devops | P0 | 3 | T-008 | DevOps |  | feature/080-observability | 2026-08-03 | 2026-08-05 | Backlog
T-081 | Load test (JMeter/k6) — 50k concurrent | D. Stabilize | devops | P0 | 3 | T-080 | DevOps |  | feature/081-loadtest | 2026-08-06 | 2026-08-10 | Backlog
T-082 | Security review (OWASP ASVS L2) | D. Stabilize | qa | P0 | 4 |  | QA |  | feature/082-security | 2026-08-03 | 2026-08-06 | Backlog
T-083 | Accessibility audit (WCAG AA) | D. Stabilize | qa | P0 | 2 |  | QA |  | feature/083-a11y | 2026-08-07 | 2026-08-10 | Backlog
T-084 | Integration/regression test (ITC-001~) | D. Stabilize | qa | P0 | 5 |  | QA |  | feature/084-regression | 2026-08-11 | 2026-08-17 | Backlog
T-085 | App Store / Play Console submission prep | D. Stabilize | release | P0 | 3 | T-084 | PM |  | feature/085-submission | 2026-08-18 | 2026-08-20 | Backlog
T-086 | Go-live runbook + incident playbook | D. Stabilize | devops | P0 | 2 | T-080 | DevOps |  | feature/086-runbook | 2026-08-21 | 2026-08-24 | Backlog
T-087 | Customer support workflow + FAQ | D. Stabilize | cs | P1 | 2 |  | CS |  | feature/087-cs | 2026-08-25 | 2026-08-26 | Backlog
TOTAL |  |  |  |  | 144

## Milestones
ID | Name | Target Date | Required Tasks | Exit Criteria
M1 | Setup Complete | 2026-05-02 | T-001..T-011 | CI/CD green, login E2E
M2 | Catalog Ready | 2026-05-30 | T-020..T-028 | Profile/Heart/Follow/FanClub E2E
M3 | Chat & Shop Ready | 2026-07-04 | T-040..T-049 | Chat + PhotoCard checkout E2E
M4 | Audition Ready | 2026-08-01 | T-060..T-068 | Round vote E2E, ranking cron OK
M5 | GA (Release) | 2026-08-29 | T-080..T-087 | Integration test PASS, store approval

## TestCases
TC ID | Type | Feature (FR) | Title | Pre-condition | Steps | Expected | Priority | Linked Task
TC-001 | Unit | FR-001 | Email signup success | No account with email X | 1) POST /auth/signup with unique email 2) receive verification 3) verify | 201 Created, verify link works | High | T-009
TC-002 | Unit | FR-001 | Signup conflict (duplicate email) | Email X already exists | POST /auth/signup with X | 409 Conflict | High | T-009
TC-003 | Unit | FR-001 | Under-age signup blocked | Birthdate=today-13y | POST /auth/signup | 422 UNDER_AGE | High | T-009
TC-004 | Unit | FR-001 | Kakao OAuth token accepted | Valid kakao id_token | POST /auth/social | 200 OK with tokens | High | T-009
TC-010 | Unit | FR-003 | Idol list pagination | 99 idols seeded | GET /idols?page=1&size=20 | 20 rows, nextCursor set | High | T-020
TC-011 | Unit | FR-003 | Idol list cache hit | Second consecutive call | Inspect Redis key catalog:idols:* | TTL > 0, DB not hit | Med | T-020
TC-012 | Unit | FR-003 | Idol detail returns media | Idol has 3 media assets | GET /idols/:id | 200 with media[] length 3 | High | T-020
TC-015 | Unit | FR-004 | Heart idempotent | User already hearted | POST /idols/:id/heart x2 | heartCount unchanged after 2nd | High | T-021
TC-016 | Unit | FR-005 | Follow toggles correctly | User not following | follow, then unfollow | State transitions visible in /me/follows | High | T-021
TC-020 | Unit | FR-006 | Join fan club creates chat room | Not yet member | POST /fan-clubs/:id/join | Membership + chat_room created with 5 daily coupons | High | T-022,T-041
TC-030 | Unit | FR-007 | Chat message consumes coupon | balance=5 | ws chat:send | balance=4, message delivered | High | T-041
TC-031 | Unit | FR-007 | Chat blocked when balance=0 | balance=0 | ws chat:send | 402 NO_COUPON | High | T-041
TC-032 | Unit | FR-008 | Auto message does not deduct | Cron fires auto-msg | Observe coupon balance | No change | High | T-042
TC-033 | Unit | FR-007 | Profanity filter blocks message | Text contains banned word | ws chat:send | 400 FILTERED + no insert | Med | T-040
TC-034 | Unit | FR-009 | Buy chat coupon 30 add | Valid receipt for pkg=30 | POST /orders/verify | balance += 30 | High | T-043
TC-035 | Perf | NFR-002 | Chat delivery < 1s p95 | 200 active WS clients | k6 WS send | p95 < 1000ms | High | T-081
TC-040 | Unit | FR-010 | Photo card random draw | set has 12 items | POST /shop/cards/:setId/buy | User gets exactly 1 card, order linked | High | T-045
TC-041 | Unit | FR-010 | Duplicate purchase allowed | Same set bought twice | Two purchases | Both cards saved, may duplicate | Med | T-045
TC-042 | Unit | FR-010 | Receipt reuse rejected | Same tx_id submitted twice | POST /orders/verify twice | Second call 409 DUPLICATE_RECEIPT | High | T-044
TC-043 | UI | FR-012 | Instagram share watermark visible | Any owned card | Share via OS sheet | Image includes logo + idol name | Med | T-048
TC-050 | Unit | FR-013 | Cast vote decrements tickets | balance=10, amount=3 | POST /audition/rounds/:id/vote | balance=7, votes row inserted | High | T-063
TC-051 | Unit | FR-013 | Insufficient tickets rejected | balance=2, amount=3 | POST vote | 402 NOT_ENOUGH | High | T-063
TC-052 | Unit | FR-013 | Vote after deadline rejected | Round ended 1s ago | POST vote | 409 ROUND_CLOSED | High | T-063
TC-053 | Unit | FR-014 | Weight validation enforced | rule sum=0.98 | Create VoteRule | 400 INVALID_WEIGHTS | High | T-061
TC-054 | Perf | NFR-004 | 50k concurrent votes | Staging pumped traffic | k6 scenario | p95 < 800ms, 0 lost | High | T-081
TC-055 | Unit | FR-016 | Rankings refresh every 5 min | Cron enabled | Wait 5 min after votes | round_rankings updated, rank set | High | T-064
TC-060 | Unit | FR-017 | Marketing push blocked at 22:00 | push_opt_in=true | Schedule marketing push | Deferred to 09:00 | Med | T-042
TC-101 | UI | FR-102 | CMS idol edit propagates in 60s | Published idol | Edit profile name | Mobile detail shows new name ≤60s | High | T-026
TC-104 | UI | FR-104 | Cannot open round before close of prior | R1 active | Attempt open R2 | Blocked w/ validation error | High | T-067
TC-105 | UI | FR-105 | Cannot edit vote rule after round start | Round active | Try edit rule | Disabled, draft only | High | T-067
TC-107 | UI | FR-107 | Analytics CSV export | Data in range | Export button | CSV with correct headers, ≤5 min delay | Med | T-068
ITC-001 | Integration | FR-001..FR-006 | New user onboarding end-to-end | Fresh device | Signup → browse idols → heart → follow → join fan club | User reaches chat room with 5 coupons | High | T-084
ITC-002 | Integration | FR-007..FR-009 | Chat + coupon lifecycle | Member | Send 5 msgs → buy coupon → send 3 more | Balance flows correctly, AI replies received | High | T-084
ITC-003 | Integration | FR-010..FR-012 | Photo card purchase + share | Member | Buy 3 sets → view collection → share 1 | 3 cards owned, share works | High | T-084
ITC-004 | Integration | FR-013..FR-016 | Audition voting lifecycle | Round active | Buy tickets → cast 3 times → view rankings | Vote counted, ranking visible ≤5min | High | T-084
ITC-005 | Regression | All | Existing regression pack | After each sprint | Full RN + CMS regression suite | No P0/P1 fails | High | T-084

## API
Method | Path | Auth | Description | Module | Linked FR
POST | /auth/signup | Public | Email signup | identity | FR-001
POST | /auth/login | Public | Email login | identity | FR-001
POST | /auth/social | Public | Social login (Apple/Google/Kakao) | identity | FR-001
POST | /auth/refresh | Refresh | Rotate refresh token | identity | FR-001
GET | /me | JWT | Current user profile | identity | FR-002
PATCH | /me | JWT | Update nickname / instagram | identity | FR-002
GET | /idols | JWT | List idols | catalog | FR-003
GET | /idols/:id | JWT | Idol detail | catalog | FR-003
POST | /idols/:id/heart | JWT | Heart / unheart | fandom | FR-004
POST | /idols/:id/follow | JWT | Follow / unfollow | fandom | FR-005
POST | /fan-clubs/:id/join | JWT | Join fan club | fandom | FR-006
DELETE | /fan-clubs/:id/leave | JWT | Leave fan club | fandom | FR-006
GET | /me/chat-rooms | JWT | My chat rooms | chat | FR-007
GET | /chat/:roomId/messages | JWT | Paginated messages | chat | FR-007
WS | /ws/chat | JWT | Chat socket (send/receive/typing) | chat | FR-007
GET | /me/coupons | JWT | Chat coupon balance | chat | FR-009
POST | /orders/verify | JWT | IAP receipt verify | commerce | FR-010/FR-015
GET | /shop/cards | JWT | Photo card sets list | commerce | FR-010
POST | /shop/cards/:setId/buy | JWT | Buy (draw) a card | commerce | FR-010
GET | /me/cards | JWT | My card collection | commerce | FR-011
POST | /cards/:id/share | JWT | Generate share image | commerce | FR-012
GET | /auditions/current | JWT | Current audition + rounds | audition | FR-013
GET | /audition/rounds/:id | JWT | Round detail | audition | FR-013
POST | /audition/rounds/:id/vote | JWT | Cast vote | audition | FR-013/FR-014
GET | /audition/rounds/:id/rankings | JWT | Rankings snapshot | audition | FR-016
POST | /shop/tickets/buy | JWT | Buy vote tickets | commerce | FR-015
POST | /push/tokens | JWT | Register push token | notification | FR-017
GET | /me/notifications | JWT | Notifications list | notification | FR-017
GET | /me/orders | JWT | Purchase history | commerce | FR-018
POST | /admin/login | Public | Admin login | adminops | CMS auth
GET | /admin/idols | Admin | List idols | adminops | FR-102
POST | /admin/idols | Admin | Create idol | adminops | FR-102
PATCH | /admin/idols/:id | Admin | Update idol | adminops | FR-102
POST | /admin/auto-messages | Admin | Set auto message template | adminops | FR-103
POST | /admin/auditions | Admin | Create audition | adminops | FR-104
POST | /admin/audition/rounds | Admin | Create round | adminops | FR-104
PATCH | /admin/audition/rounds/:id | Admin | Open/close round | adminops | FR-104
POST | /admin/vote-rules | Admin | Create vote rule | adminops | FR-105
GET | /admin/analytics/votes | Admin | Vote aggregates | adminops | FR-107
GET | /admin/analytics/revenue | Admin | Revenue aggregates | adminops | FR-107
GET | /admin/users | Admin | User search | adminops | FR-110

## Screens
Screen ID | Platform | Name | Route | Auth | Notes
SCR-MOB-001 | Mobile | Splash / Onboarding | /splash | Public | 3p guide
SCR-MOB-002 | Mobile | Sign-in | /auth/sign-in | Public | Social + email
SCR-MOB-003 | Mobile | Sign-up Extra | /auth/profile-setup | Auth | Nickname / birth
SCR-MOB-010 | Mobile | Home (Discover) | /tabs/home | Auth | Feed + banner
SCR-MOB-011 | Mobile | Idol List | /tabs/idols | Auth | 99 grid
SCR-MOB-012 | Mobile | Idol Detail | /idols/:id | Auth | Heart/Follow/Join
SCR-MOB-020 | Mobile | My Fan Clubs | /tabs/my-clubs | Auth | joined list
SCR-MOB-030 | Mobile | Chat Room | /chat/:roomId | Auth+Member | WS
SCR-MOB-031 | Mobile | Coupon Purchase Modal | overlay | Auth | Packages
SCR-MOB-040 | Mobile | Photo Card Shop | /shop/cards | Auth
SCR-MOB-041 | Mobile | Draw Result | overlay | Auth | Animation
SCR-MOB-042 | Mobile | My Collection | /me/cards | Auth
SCR-MOB-050 | Mobile | Audition Overview | /tabs/audition | Auth
SCR-MOB-051 | Mobile | Round Vote | /audition/:roundId | Auth
SCR-MOB-052 | Mobile | Vote Ticket Shop | /shop/tickets | Auth
SCR-MOB-053 | Mobile | Rankings | /audition/:roundId/rankings | Auth
SCR-MOB-060 | Mobile | Profile / Settings | /tabs/me | Auth
SCR-CMS-001 | CMS | Admin Login | /login | Public | MFA
SCR-CMS-002 | CMS | Dashboard | / | Admin | Summary
SCR-CMS-010 | CMS | Idol Manager | /idols | content_admin
SCR-CMS-011 | CMS | Idol Detail/Edit | /idols/:id | content_admin
SCR-CMS-012 | CMS | Agency Manager | /agencies | content_admin
SCR-CMS-013 | CMS | Auto Message Templates | /chat/templates | content_admin
SCR-CMS-020 | CMS | Audition Manager | /auditions | audition_admin
SCR-CMS-021 | CMS | Vote Rule Editor | /auditions/:id/rules | audition_admin
SCR-CMS-022 | CMS | Round Monitor | /auditions/:id/rounds/:rid | audition_admin
SCR-CMS-030 | CMS | Analytics | /analytics | super_admin
SCR-CMS-031 | CMS | Photo Card Sets | /cards | content_admin
SCR-CMS-040 | CMS | User CS Console | /users | cs_admin
SCR-CMS-041 | CMS | Report Queue | /reports | cs_admin

## Risks
ID | Risk | Likelihood | Impact | Score | Owner | Mitigation
R-01 | App store / Play review delay | H | H | 16 | PM | Pre-submission 2 weeks early, policy docs
R-02 | Audition traffic spike | M | H | 12 | Backend | Redis counter + BullMQ agg + partition + load test W16
R-03 | Receipt forgery / reuse | M | H | 12 | Backend | receipts UNIQUE + server verify + Idempotency-Key
R-04 | AI idol reply quality | M | M | 9 | Backend | MVP templated pool + Phase2 LLM
R-05 | 99 idol seeding delay | M | M | 9 | Content | Contract early + parallel sample data
R-06 | RN version compatibility | L | M | 6 | Mobile | Pin 0.74, upgrade outside sprint
R-07 | SMS vote vendor uncertainty | H | M | 12 | PM | ADR-004 stub for MVP, finalize before finals

## KPI
KPI | Definition | Target (T+3mo) | Source | Frequency
DAU | Unique users active in the day | 20,000 | BI table user_activity | Daily
D30 Retention | % users returning within 30 days | 25% | cohort_retention | Weekly
Fan Club Conversion | Members / logged-in users | 15% | memberships | Weekly
ARPPU | Revenue / paying users | ₩15,000 /mo | orders | Weekly
Audition Participation | Voters / MAU | 40% | votes, users | Per round
Coupon Repurchase | Users with >=2 coupon orders | 10% | orders | Weekly
Crash-free users | Sessions without crash | 99.8% | Sentry | Daily
API p95 | 95th percentile latency | <300ms | Datadog APM | Real-time